## Sheet1
Risk No. | Risk item | Effect | Cause | Probability | Severity | Matrix Value | Actions to Minimize Risks | Final review
Project Planning
1.1.1 | Setting unrealistic deadlines and milestones | Poor planning and authorisation with clients can damage relationship with clients AND team members. Doing so can also impact the end results of particular features. | Poor planning and communication between parties. Little experience of new tools | 2 | 4 | 8 | Consult throughly with client to understand all of the project requirements indepth. Target a minimal viable product with goals set around that first, with more added later if possible.
1.1.2 | Poor judgement of ability | By not beign realistic with your own exisiting knowledge and ability, the quality and chance of deliverance can be massively affected. Worst case scernio would mean that the minimal viable product can not be achieve ultimately failing the project. | Little experience using new tools. Overconfident with regards to planning, leaving little time to complete tasks. | 1 | 4 | 4 | Apply yourself to each lecture session and use the various lesson recordings to my advantage. Use the support of my trainer and team mates to get adjusted to the new tools and help others along the way.
1.1.3 | Change in project specification | depending on the lateness of a change, as well as the serious of said change, this will massive effect the project from all aspects from architecture, to methodologies used. This in combination with other risks can cause massive issues | Change in requirements from internal/external sources. | 1 | 5 | 5 | plan ahead for extra time to complete said changes. Priortise particular features and parts that may be less vunerable for change. Organise a deadline extenision for the project.
Project Development
1.2.1 | Poor accessibility to appropriate software/ hardware | Poor or no access to related hardware and/or software can effect both the accessibility of the project. files, as well as the progression towards expected milestones. | Limited access to sufficient machines, little to no cloud storage capability, downtime on related services and privacy concerns. | 1 | 2 | 2 | Provide access and resources to efficient hardware and software that allow developers to fufill their projects. Setup remote access to related platforms and documents.
1.2.2 | Poor internet access/connection | Poor internet access or access can prohibate my acess to learning content, VM access and video meetings, which can impact various areas from project progression, relationship management and learning potential | Poor location regarding connection, low bandwidth in household, wireless connection as appose to wired. | 4 | 4 | 16 | Have alternatives to existing internet connection such as mobile hotstops and access to public internet. Little can be done to fix household internet due to modern position, contract ect.
1.2.4 | Limited funds on Google Cloud Services | Trial funds are needed to access VM instances and SQL Databases. If those funds are depleted to zero, I will be unable to access my accout and its items witthout having to subscribe to a paid service or purchase more credits, which are very expensive | Due to using a lot for my previous project, I am already low on funds and the new project might be as or more demanding on my allowance | 3 | 4 | 12 | Turn off SQL databases and VM Instances after every session to save allowance. Reduce after hours working. If needed purchase more allowance or use an alternative GCP account with fresh allowance OR use another cloud service.
Health and Conditioning
1.3.1 | Possibility of illness | Falling ill during both the planning and development phases of the projec can result in a loss of time, as well as a drop in quality for the project. | Poor Hygiene, poor diet, stress | 2 | 1 | 2 | Continue with basic hygiene routine, eat/drink enough, take frequent breaks, use prescribed medicines if applicable, provide enough time to catch up with work. Since we are now working remotely, there has been enough material provided so we can study from anywhere in any conditions, reducing the risk of this item
1.3.3 | Posture/Ergonomics related issues | Issues regarding posture and lack of ergonic support can not only affect the long term health of a developer, it can also affect the standard of work produced due to the undesireale conditions of the developer. Both probability and severity have increased from the last project, due to new working conditions and no access to benefactory equipment. | Lack of ergonical equipment, poor working conditions | 2 | 3 | 6 | Provide developer(s) with suitable ergonic support such as workchairs, wrist supports ect.. Take and respect breaks given to us by our trainer.
1.3.4 | Distruption due to current world events | Since our previous project, remote working has been piut in place to counter the ongoing COVID-19 Pandemic. Likely risks include illness, isolation, little access to work content and even possible closure of project. | Spread of COVID-19 | 5 | 5 | 25 | Ensure that has been protocols made to ensure productivity at home or at remote locations. Establish remote communication links and potentially adjust the goals and targets to match the severity of the current scenario. Provide recording of all materials. Be understanding of some people. conditions and how they react to it.
*: severity and probabiity of most the items lists may be affected by the COVID-19 Outbreak (16/03/20)
Key: Likelihood and Impact Scale uses a 1-5 scale, with 1 being not very strong and 5 being very strong