## Sheet1
Risk No. | Risk item | Effect | Cause | Probability | Severity | Matrix Value | Actions to Minimize Risks | Final review
Project Planning
1.1.1 | Setting unrealistic deadlines and milestones | Poor planning and authorisation with clients can damage relationship with clients AND team members. Doing so can also impact the end results of particular features. | Poor planning and communication between parties. Little experience of new tools | 2 | 4 | 8 | Consult throughly with client to understand all of the project requirements indepth. Target a minimal viable product with goals set around that first, with more added later if possible. | Many of the additional marks where planned to be worked around at the start, however a later detailed explaination into the marking system ment that certain requirement could not have been met since a lot of work would have had to be done very late
1.1.2 | Poor judgement of ability | By not beign realistic with your own exisiting knowledge and ability, the quality and chance of deliverance can be massively affected. Worst case scernio would mean that the minimal viable product can not be achieve ultimately failing the project. | Little experience using new tools. Overconfident with regards to planning, leaving little time to complete tasks. | 1 | 4 | 4 | Apply yourself to each lecture session and use the various lesson recordings to my advantage. Use the support of my trainer and team mates to get adjusted to the new tools and help others along the way. | We used a lot of the same tools as the previous project, hence there was not much issue with progressing with this project. Some of the uses of docker where new but also exciting to overcome, whilst some issues with ansible where had due to its newer version
1.1.3 | Change in project specification | depending on the lateness of a change, as well as the serious of said change, this will massive effect the project from all aspects from architecture, to methodologies used. This in combination with other risks can cause massive issues | Change in requirements from internal/external sources. | 1 | 5 | 5 | plan ahead for extra time to complete said changes. Priortise particular features and parts that may be less vunerable for change. Organise a deadline extenision for the project. | The spec never changed during the development of the proeject. See first point regarding the revealing of additional marking.
Project Development
1.2.1 | Poor accessibility to appropriate software/ hardware | Poor or no access to related hardware and/or software can effect both the accessibility of the project. files, as well as the progression towards expected milestones. | Limited access to sufficient machines, little to no cloud storage capability, downtime on related services and privacy concerns. | 1 | 2 | 2 | Provide access and resources to efficient hardware and software that allow developers to fufill their projects. Setup remote access to related platforms and documents. | There was little issue for this, as we where set up remotely before this project started and everyone should have been somewhat proficient with the tools used up to this point.
1.2.2 | Poor internet access/connection | Poor internet access or access can prohibate my acess to learning content, VM access and video meetings, which can impact various areas from project progression, relationship management and learning potential | Poor location regarding connection, low bandwidth in household, wireless connection as appose to wired. | 4 | 4 | 16 | Have alternatives to existing internet connection such as mobile hotstops and access to public internet. Little can be done to fix household internet due to modern position, contract ect. | Internet was a problem due to multiple people using it in my household at the same time. However alternatives such as mobile hotspots helped me overcome this problem
1.2.3 | SQL Injection Attacks | Common hacking technique that can drastically change or destroy my database, resulting in inefficiency of project deliverables. Illegal access to database and its data. | Poor security for project. "neglegtion of code for database and input of malicious table entries and code. concerns" | 2 | 3 | 6 | Have secure access protection for the website whilst in early development. Implement strong validation rules for tables to prevent malicious attacks | Whilst this wasn’t a issue, an issue was arisen when a outside user had access to my URL and was actively using the app. No inappropriate use was done, but prompted me to research and include this risk item.
1.2.4 | Issue with currrent build of technologies | Whilst using a large array of technology and tools that are always rapidly evolving and improving, poorly tested versions of software might not be compatible with other tools and may include a lot of bugs that might jeprodise the progression of the project | Poor testing or volitile versions of the tools we will be using. Little compability between each of the tools | 2 | 2 | 4 | A lot of the tools we will be using will usually have work arounds and alternative solutions if problems occur. Research those ideas. Use the correct versions and have access to other tools incase of no solution. | Some issues where had with the current version of Ansible and I made these apparent to the client. Alternatives where made so project could continue
1.2.5 | Limited funds on Google Cloud Services | Trial funds are needed to access VM instances and SQL Databases. If those funds are depleted to zero, I will be unable to access my accout and its items witthout having to subscribe to a paid service or purchase more credits, which are very expensive | Due to using a lot for my previous project, I am already low on funds and the new project might be as or more demanding on my allowance | 3 | 4 | 12 | Turn off SQL databases and VM Instances after every session to save allowance. Reduce after hours working. If needed purchase more allowance or use an alternative GCP account with fresh allowance OR use another cloud service. | Careful management of the items in my GCP account had to be made to prevent any major loss of trial funds. This was somewhat adhered to and I will have funds to demonstrate and access my project after completion.
Health and Conditioning
1.3.1 | Possibility of illness | Falling ill during both the planning and development phases of the projec can result in a loss of time, as well as a drop in quality for the project. | Poor Hygiene, poor diet, stress | 2 | 1 | 2 | Continue with basic hygiene routine, eat/drink enough, take frequent breaks, use prescribed medicines if applicable, provide enough time to catch up with work. Since we are now working remotely, there has been enough material provided so we can study from anywhere in any conditions, reducing the risk of this item | Light illness as an issue very early in the project but did not prevent me from completing work or attending calls
1.3.3 | Posture/Ergonomics related issues | Issues regarding posture and lack of ergonic support can not only affect the long term health of a developer, it can also affect the standard of work produced due to the undesireale conditions of the developer. Both probability and severity have increased from the last project, due to new working conditions and no access to benefactory equipment. | Lack of ergonical equipment, poor working conditions | 2 | 3 | 6 | Provide developer(s) with suitable ergonic support such as workchairs, wrist supports ect.. Take and respect breaks given to us by our trainer. | Early signs of uncomfort cannot be seen and has had no impact on the project. Regular breaks where taken.
1.3.4 | Distruption due to current world events | Since our previous project, remote working has been piut in place to counter the ongoing COVID-19 Pandemic. Likely risks include illness, isolation, little access to work content and even possible closure of project. | Spread of COVID-19 | 5 | 5 | 25 | Ensure that has been protocols made to ensure productivity at home or at remote locations. Establish remote communication links and potentially adjust the goals and targets to match the severity of the current scenario. Provide recording of all materials. Be understanding of some people. conditions and how they react to it. | All of the distributions caused had happened prior and there where enough measures made prior to prevent any major impact to the project
*: severity and probabiity of most the items lists may be affected by the COVID-19 Outbreak (16/03/20)
Key: Likelihood and Impact Scale uses a 1-5 scale, with 1 being not very strong and 5 being very strong